CONTROL PACK (FREE)

Clarity. Control. Delivery.

Use these templates to stop scope creep, tighten contractor control, and run a proper weekly cadence.

How to use this pack (10 minutes)

1) Copy this file and fill the templates in order: Scope Builder -> Change Request -> Weekly Update -> Scorecard.
2) Run a weekly 30-minute control call with your contractor (same day/time each week).
3) Keep everything in one folder: photos, drawings, quotes, change requests, and weekly updates.
4) Rule: if it is not written down and agreed, it does not exist.

Suggested weekly cadence

• Monday: contractor submits plan for the week + labour forecast.
• Mid-week: quick check-in (10 mins) if access/permits are tight.
• Friday: issue Weekly Client Update + scorecard + any change requests.

Tip: Use the wording in these templates as-is. It is designed to remove ambiguity.

Template 1: 1-page Scope Builder

Fill this in before you request any quote. Attach drawings/photos if you have them.

| Project / Site | [Insert address / site location] |
| --- | --- |
| Client | [Name + contact] |
| Contractor | [Name + contact] |
| Objective | [What does success look like?] |
| Scope - Inclusions | 1) 2) 3) |
| Scope - Exclusions | 1) 2) 3) |
| Assumptions | 1) 2) |
| Constraints | Access hours, noise limits, neighbours, permits, parking, etc. |
| Materials / Specifications | Brands, finishes, tolerances, standards, warranties required. |
| Interfaces / Dependencies | Other trades, utilities, inspections, lead times. |
| Client Responsibilities | Access, information, approvals, timely decisions, payments. |
| Contractor Responsibilities | Method, H&S, quality control, protection of existing, waste removal. |
| Quality / Acceptance Criteria | Snag standard, test certificates, commissioning, handover pack. |
| Programme Milestones | Start: Key milestone: Completion: |
| Payment Milestones | Deposit: Interim: Completion: |
| Change Control Rule | Any change must be raised on Template 2 and agreed (time/cost) before work proceeds. |
| Sign-off | Client name/sign/date: Contractor name/sign/date: |

Optional: Add a simple sketch/photo markup showing exactly what is included.

Template 2: Change Request (Variation) Form

Use this anytime scope changes or a surprise is found. No form = no change.

| Change Request ID | CR-001 |
| --- | --- |
| Date Raised | [DD/MM/YYYY] |
| Raised By | [Name / company] |
| Description of Change | [What is changing and why?] |
| Reason (tick) | ☐ Client request ☐ Design development ☐ Unforeseen condition ☐ Compliance ☐ Other |
| Impact - Cost | £[ ] (labour/materials/plant) + VAT (if applicable) |
| Impact - Time | [ ] working days / revised completion date: [ ] |
| Impact - Quality / Spec | [Any change in finish, warranty, standard?] |
| Options (if any) | Option A: £ / days Option B: £ / days |
| Quote / Evidence Attached | ☐ Photo ☐ Drawing ☐ Supplier quote ☐ Breakdown |
| Decision Required By | [DD/MM/YYYY] |
| Approval | Client: Approved / Rejected (circle) Name/Sign/Date: Contractor: Name/Sign/Date: |
| Instruction | Work must not proceed until approved in writing. |

Template 3: Weekly Client Update (1 page)

Send this the same time every week. Keep it factual and short.

| Project | [Name / address] |
| --- | --- |
| Week Ending | [DD/MM/YYYY] |
| Overall Status (RAG) | ☐ Green (on track) ☐ Amber (at risk) ☐ Red (off track) |
| Progress this week | • • • |
| Plan next week | • • • |
| Decisions needed from client | 1) 2) |
| Risks / Issues (top 3) | - Risk/Issue: Mitigation: 2) 3) |
| Changes this week | CRs raised/approved: CR-__ / CR-__ Cost/time impact summary: |
| Commercial | Paid to date: £[ ] Outstanding: £[ ] Forecast at completion: £[ ] |
| Quality / Snags | Snags raised: [ ] Snags closed: [ ] Notes: |
| Photos / Evidence | [Insert link to folder / attach key photos] |

Template 4: Contractor Performance Scorecard (Weekly)

Score 1-5 (1 = poor, 3 = acceptable, 5 = excellent). Use this to drive behaviour.

| Category | Score (1-5) | Evidence / Examples | Actions / Owner / Due |
| --- | --- | --- | --- |
| Safety & site control (housekeeping, access, protection) | [ ] | [ ] | [ ] |
| Programme reliability (does the plan happen?) | [ ] | [ ] | [ ] |
| Quality (first-time right, snags) | [ ] | [ ] | [ ] |
| Communication (updates, responsiveness) | [ ] | [ ] | [ ] |
| Commercial discipline (quotes, breakdowns, change control) | [ ] | [ ] | [ ] |
| Resource management (labour levels, supervision) | [ ] | [ ] | [ ] |
| Client impact (noise, neighbours, cleanliness) | [ ] | [ ] | [ ] |

Trigger points:
• If any category is 2 or below: agree a corrective action within 48 hours.
• If 2 or below repeats for 2 weeks: issue a formal notice / consider replacement.

Optional add-ons (use if you want more control)

A) Kick-off agenda (30 minutes)

1) Confirm scope (Template 1) and exclusions.
2) Confirm programme milestones and access constraints.
3) Confirm communication rules (Template 3 weekly update cadence).
4) Confirm change control (Template 2) and approval authority.
5) Confirm quality standard and handover requirements.
6) Confirm payment milestones and evidence required for payment.

B) Decision log (simple)

| Date | Decision | Options considered | Owner | Due |
| --- | --- | --- | --- | --- |
| [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] |

© SCOPE Project Delivery | Free to use. Do not sell these templates as standalone products.